## Sheet1
Library Mangement System Product Backlog
NO | As a | I want to be able to | So that | Priority | Sprint | Status
1 | As a library Admin | I want to make an account in the system | So I can log in and access into the system and aunthorized users shoud not be able to login to the system | Must | 1 | Done
2 | As a library Admin | I want to have a dashboard | So I can easiy access all the options available in the system | Must | 1 | Done
3 | As a library Admin | I want to have a centrazlied database for my library | so I could retrieve information and manage them. | Must | 1 | Done
4 | As a library Admin | I want to add books to our system | I can system to keep track of our library books | Must | 1 | Done
5 | As a library Admin | I want the users to be friendly | So I can learn and interact more efficiently | Must | 1 | Done
6 | As a library Admin | I want to see the list of books issued to users | so I know which books are not available at the time. | Should | 2 | Work in Progress
7 | As a library Admin | I want to know the due dates for the books | so I notify users to return them | Should | 2 | Work in Progress
8 | As a library Admin | I want to quick search for my books | So I can find them faster | Must | 2 | Work in Progress
9 | As a library Admin | I want to retrieve information who took a particular book and which books are available in the library | so I can track all the books. | Shoud | 2 | Work in Progress
10 | As a library Admin | I want to update the details about a particular book | so I can have all the accurate information related to the books. | Must | 2 | Work in Progress
11 | As a library Admin | I want to delete a book when they are lost or outdated | so I can have an accurate number of books. | Must | 3 | To Be started
12 | As a library Admin | I want to add users to our library database | so we could issue them a book or use our services. | Should | 3 | To Be started
14 | As a library Admin | I want to categorize the books based on their types | So I can search for them faster. | Must | 3 | To Be started
15 | As a library Admin | I want to search for a book | so I can access it faster and easier. | Must | 3 | To Be started
16 | As a library Admin | I want to delete a user when they cancel their membership with us | so I could keep track of our real customers. | Must | 4 | To Be started
17 | As a library Admin | I want to see a separate list of magazines, newspaper and books | So I can track the books and magazines separetly. | Must | 4 | To Be started
18 | As a library Admin | I want to be able to print preview books and magazines | So I can print them whenever needed | Should | 4 | To Be started
19 | As a library Admin | I want to filter my books/magazines | So I can find them faster | Should | 4 | To Be started
20 | As a library Admin | I want to issue a book to a user | so I know which users have the books | Must | 5 | To Be started
21 | As a library Admin | I want to export all my books and magazines to A CSV file | So I can have a backup of my books if the system crashes | Should | 5 | To Be started
22 | As a library Admin | I want to be able to logout of the system | So no one else can access the system without any username | Must | 5 | To Be started