## Sprint 1
Sprint One – October 9 to October 12, 2020
| Tasks | Hours | Day 1 | Day 2 | Day 3 | Day 4
1 | Create a Sign-Up Page | 2 | 2
2 | Create a Log-In Page | 2 | 2
3 | Create a Database for the users' Log-in Info | 2 |  | 2
4 | Design a user-friendly Dashboard | 2 |  | 2
5 | Implement the design of the Dashboard | 2 |  | 2
6 | Ensure the System is effiecient to use | 2 |  |  | 2
7 | Provide "Add Books" option in the System and in the Database | 4 | 2 |  | 2
8 | Design and create a Database for the users' info | 4 |  |  |  | 2
| Total Hours: | 20 | 6 | 6 | 4 | 2
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Estimated Effort | 20 | 16 | 12 | 8 | 4 | 0
| Actual Effort | 20 | 6 | 6 | 4 | 2 | 0

## Sprint 2
Sprint Two – October 13 to October 16, 2020
| Tasks | Hours | Day 1 | Day 2 | Day 3 | Day 4
1 | Design and create a "list-view" in the interface | 4 | 4
2 | Create and design notification systems | 4 | 2 | 2
3 | Create a Quick Search option for retrieval of books | 4 |  | 4
4 | Enhance the Quick Search Option by adding more relevant features based on the information of the books | 4 |  |  | 4
5 | Include an Edit Option for the users as well as the books | 4 |  |  | 2 | 2
| Total Hours: | 20 | 6 | 6 | 6 | 2
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Estimated Effort | 20 | 16 | 12 | 8 | 4 | 0
| Actual Effort | 20 | 6 | 6 | 6 | 2 | 0

## Sprint 3
Sprint Three – October 17 to October 20, 2020
| Tasks | Hours | Day 1 | Day 2 | Day 3 | Day 4
1 | Implement a “Delete Option” for books | 4 | 4
2 | Allow “Add Option” to the Admin to add users in the Database | 4 | 2 | 2
3 | Design and create check-in and out of books through members whose data are in the database | 4 |  | 4
4 | Include option of “Genre” on Quick Search Option | 4 |  |  | 4
5 | Enhance the “Quick Search” Option | 4 |  |  | 2 | 2
6 | Total Hours: | 20 | 6 | 6 | 6 | 2
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Estimated Effort | 20 | 16 | 12 | 8 | 4 | 0
| Actual Effort | 20 | 6 | 6 | 6 | 2 | 0

## Sprint 4
Sprint Four – October 21 to October 24, 2020
| Tasks | Hours | Day 1 | Day 2 | Day 3 | Day 4
1 | Add a “Delete Option” for the Admin to be able to delete users | 4 | 4
2 | Design and create “List-view” for each category | 4 | 2 | 2
3 | Include “Print Option” for the materials in the system | 4 |  | 4
4 | Ensure the printing is legally allowed | 4 |  |  | 4
5 | Add a “Filter Option” for the materials in the system | 4 |  |  | 2 | 2
6 | Total Hours: | 20 | 6 | 6 | 6 | 2
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Estimated Effort | 20 | 16 | 12 | 8 | 4 | 0
| Actual Effort | 20 | 6 | 6 | 6 | 2 | 0

## Sprint 5
Sprint Five – October 25 to October 28, 2020
| Tasks | Hours | Day 1 | Day 2 | Day 3 | Day 4
1 | Give admin the privilege to approving or denying a check-in of books | 5 | 1 | 1 | 1 | 1
2 | Create an “Export Option” | 5 | 5
3 | Create CSV File in the database exclusively for the Export Option | 5 |  | 5
4 | Secure the system by logging out the admin and the user whenever they leave the system | 5 |  |  | 5
6 | Total Hours | 20 | 6 | 6 | 6 | 1
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
| Estimated Effort | 20 | 16 | 12 | 8 | 4 | 0
| Actual Effort | 20 | 5 | 5 | 5 | 5 | 0